## Sheet1
Project Stage | Task | Assigned to: | Notes | Date of Completion | Deadline | Reason for Delay | Jira Ticket | Git Commit tag | Completion Date Coloring Schema:
Planning and Organization | Team Organization Meeting | All |  | 2020-06-03 | 2020-06-03 |  | N/A | 7d835fe | Done ahead of schedule
| Github Repository Structure | Devon | Add ignore files and branch rules | 2020-06-09 | 2020-06-04 | Branching strategy joint review 6/8 |  |  | Done on schedule
| Project Schedule Finalization | All | Review with Ravi | 2020-06-04 |  |  |  | 7e5e145 | Done behind schedule
| Project Division and Module Assignments | All |  | 2020-06-08 | 2020-06-05 | Jira Setup |  |  | To Do
| Create Coding, Req, and Configuration Standards | All | Shared across teams | 2020-06-05 |  |  |  |  | Overdue
| Jira Setup |  |  | 2020-06-08 |  | Refining as per manager suggestions
Research and Functionality Descriptions | Specification Review | All | Additions discussed during joint team meeting on 6/4/2020 | 2020-06-05 | 2020-06-08 |  |  | e02e6e4
| Specification Edits Documentation | All |  | 2020-06-05 |  |  | SWATCH1-140
| Functionality Descriptions | Per Module Assignment |  | 2020-06-08 |  |  | SWATCH1-101, 102, 103, 104
| Learning Verilog | All |  | 2020-06-11 | 2020-06-10 | HR mandatory training | SWATCH1-105, 106, 107, 108 |  | Team Organization
Requirements Generation | General Requirements | Devon | Reviewed by: Antonio | 2020-06-12 | 2020-06-11 | Github merging issues. Formatting discrepancies not addressed in standards. | SWATCH1-109, 110 | 22e413f | Team Lead: Waseem
| Trigger Detection Requirements | Antonio | Reviewed by: Harry |  |  |  | SWATCH1-111, 112 |  | Github Admin: Devon
| 10ms Timer Requirements | Harry | Reviewed by: Devon |  |  |  | SWATCH1-113, 114 |  | Verilog Expert: Antonio
| 20-bit Decimal Counter Requirements | Devon | Reviewed by: Waseem |  |  |  | SWATCH1-115, 116 |  | Documentation: Harry
| 7-Segment Adapter Requirements | Waseem | Reviewed by: Antonio |  |  |  | SWATCH1-141, 145
| 7-Segment Driver Requirements | Waseem | Reviewed by: Antonio |  |  |  | SWATCH1-117, 118
Stage 1: Module Development | Trigger Detection Circuit | Antonio |  |  | 2020-06-12 |  | SWATCH1-53
| 10 ms Timer Results Documentation | Harry |  |  |  |  | SWATCH1-26
| 20-bit Decimal Up Counter | Devon |  |  |  |  | SWATCH1-56
| 7 Segment Adapter Module | Waseem |  |  |  |  | SWATCH1-142
| 7-Segment Display Module | Waseem |  |  |  |  | SWATCH1-28
Stage 2: Module Verification | Trigger Detection Test Cases | Harry | Reviewed by: Antonio |  | 2020-06-15
Trigger Detection Test Bench
| 10 ms Timer Test Cases | Devon | Reviewed by: Harry
10 ms Timer Test Bench
| 24-bit Counter Test Cases | Waseem | Reviewed by: Devon
24-bit Counter Test Bench
| 7-Segment Display Module Test Cases | Antonio | Reviewed by: Waseem
7-Segment Display Module Test Bench
| Trigger Detection Results Documentation |  |  |  | 2020-06-16
10 ms Timer Results Documentation
20-bit Decimal Up Counter Results Documentation
7-Segment Display Module Test Documentation
Stage 3: Top Level Implementation | Top Level Wrapper / Port Mapping | Antonio |  |  | 2020-06-17
Stage 4: Functional Verification | Top Level Test Bench Creation | Harry
| Simulation Results Documentation | Waseem
Stage 5: Synthesis and FPGA Implementation | Constraints File Creation | Devon
| Implementation | Waseem |  |  | 2020-06-18
| STA and Power Analysis | Waseem
Stage 6: Final | Documentation Finalization | All
| Debrief | All