## Sheet1
Project Stage | Task | Assigned to: | Notes | Date of Completion | Deadline | Reason for Delay | Action Taken | Git Commit tag | Completion Date Coloring Schema:
Planning and Organization | Team Organization Meeting | All |  | 2020-06-03 | 2020-06-03 |  |  | 7d835fe | Done ahead of schedule
| Github Repository Structure | Devon | Add ignore files and branch rules | 2020-06-09 | 2020-06-04 | Branching strategy joint review 6/8 |  |  | Done on schedule
| Project Schedule Finalization | All | Review with Ravi | 2020-06-04 |  |  |  | 7e5e145 | Done behind schedule
| Project Division and Module Assignments | All |  | 2020-06-08 | 2020-06-05 | Jira Setup |  |  | To Do
| Create Coding, Req, and Configuration Standards | All | Shared across teams | 2020-06-05 |  |  |  |  | Overdue
| Jira Setup |  |  | 2020-06-08 |  | Refining as per manager suggestions
Research and Functionality Descriptions | Specification Review | All | Additions discussed during joint team meeting on 6/4/2020 | 2020-06-05 | 2020-06-08 |  |  | 7e5e145
| Specification Edits Documentation | All |  | 2020-06-05
| Functionality Descriptions | Per Module Assignment |  | 2020-06-08
| Learning Verilog | All |  | 2020-06-11 | 2020-06-10 | HR mandatory training |  |  | Team Organization
Requirements Generation | Trigger Detection Requirements | Antonio | Reviewed by: |  | 2020-06-11 |  |  |  | Team Lead: Waseem
| 10ms Timer Requirements | Harry | Reviewed by: | [5 empty] | Github Admin: Devon
| 20-bit Decimal Counter Requirements | Devon | Reviewed by: | [5 empty] | Verilog Expert: Antonio
| 7-Segment Display Requirements | Waseem | Reviewed by: | [5 empty] | Documentation: Harry
Stage 1: Module Development | Trigger Detection Circuit | Antonio |  |  | 2020-06-12
| 10 ms Timer Results Documentation | Harry
| 20-bit Decimal Up Counter | Devon
| 7-Segment Display Module | Waseem
Stage 2: Module Verification | Trigger Detection Test Bench | Antonio |  |  | 2020-06-15
| 10 ms Timer Test Bench | Harry
| 20-bit Decimal Up Counter Test Bench | Devon
| 7-Segment Display Module Test Bench | Waseem
| Trigger Detection Results Documentation | Antonio |  |  | 2020-06-16
| 10 ms Timer Results Documentation | Harry
| 20-bit Decimal Up Counter Results Documentation | Devon
| 7-Segment Display Module Test Documentation | Waseem
Stage 3: Top Level Implementation | Top Level Wrapper / Port Mapping | Antonio |  |  | 2020-06-17
Stage 4: Functional Verification | Top Level Test Bench Creation | Harry
| Simulation Results Documentation | Waseem
Stage 5: Synthesis and FPGA Implementation | Constraints File Creation | Devon
| Implementation | Waseem |  |  | 2020-06-18
| STA and Power Analysis | Waseem
Stage 6: Final | Documentation Finalization | All
| Debrief | All